## Revision History
Document Name: KVB_Lessons Learnt_1.0
Ver. No. | Date | Prepared By | Reviewed By | Approved By | Changes made (affected sections)
1 | 2018-06-01 | Asok Kumar | Thirumoorthy | Thirumoorthy | Initial Version
Template Release Log Sheet
Ver. No. | Date | Prepared By | Reviewed By | Approved By | Changes made (affected sections)
1 | 2004-07-14 | PMO | PMO | PMO | Initial Version
1.1 | 2007-01-22 | PMO | PMO | PMO | Updated the template release log sheet

## Instructions
Lesson Learned Template
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each change request identified, complete the following:
A | ID: A unique ID number used to identify the lesson learned in the lesson learned log.
B | Date Identified: This column should be populated with the date that the lesson learned was identified.
C | Entered By: This column should be populated with the name of the individual who identified the lesson learned.
D | Subject: This column should be populated with a brief attention grabbing headline that describes the subject of the lesson learned.
E | Situation: This column should be populated with a detailed description of the situation learned from.
F | Lesson Learned & Recommendations: This column should be populated with a description of the lesson learned from the situation described in column E and the corrective action taken. Include recommendations regarding the outcome of the corrective action, good or bad, to help guide future project managers.
G | Follow-Up Needed: Indicates whether or not additional follow-up is needed.
Column | Instructions for Changing the Contents of Drop-Down Menus
N/A | Highlight the cell where you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field.
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on. From the file menu click "Date" -> "Filter" ->"Auto Filter". Then select your filter criteria from the drop down menu that appears on your header cell.

## Lessons_Learned_Log
LESSONS LEARNED LOG
Project Name: |  |  | KVB
Project Manager Name: |  |  | Vijay Bhaskar
Project Description: |  |  | BCT would provide support on migration activities by enabling required tools to convert the old services into new which will be running on new ESB platform. Migration activity does not include any new services / functionalities to add into new environment. At the end of the migration, it provide a new migrated environment which makes sure that all the functionalities are working as similar to older version. In addition to above that, below activities are involved as part of migration.  Development / UAT/ production environment setup  Planned training session to developers  SIT testing activities  UAT testing activities  Go-live
ID | Date Identified | Entered By | Subject | Situation | Recommendations & Comments | Follow-Up Needed? | Status
1 | 24th April 2018 | Asok Kumar | In KVB environment, there is a issue where all sckets are blocked when IB server is down. After that none of the messages are processing at ESB server | In KVB environment, the treads are blocked at some point of time when the IB server is down. The main reason is that all the connections are alive at some point of time and slowly closing. The thread has to be closed immediately then only it has to bear the incomming request from channels. | In WAS server the minimum thread configuration was 50, ie, why the blockage has happened when server is down. When the thread configuration was increased ie, 1200, the problem was resolved. | No | Closed
2 | 18th Jan 2021 | Divahar | In DMS API many file are not uploded due to session invalid | DMS API used by multiple modules Service request, Aadhaar Validation and CPPS. While upload more than one document cuncurently, only one document get uploded successfully, other documents are not uploaded | We have recommendated to change design instead of login into DMS API, Login only one time and use the token to get failure. IF token get fail again need to login | No | Closed
3 | 12th Jun 2020 | Divahar | Customer 360 API taking more time to respond | mobile home screen not loded customer whose having multiple account | We are recommendated use clob read method from DB instead of char | No | Closed
4 | 9th Feb 2021 | Kiruthika | Duplicate account opend Dlite app in Production | Customer submitted the final stage in two times in milliseconds that time Exist account opened two times in Mobile appication Dlite app. | We have customised the table entry in duplicate check,once sumbit the final stage checked the table entry in millseconds before CBS api calling. | No | Closed
5 | 31st aug 2019 | Kiruthika | CustomerIC already exists for another customer id cbs issue coming in Account opening | customer ic generate 14 digits first five letter of customer name and 8 digits is ddmmyyyy and the 1 digit is male or female (M or F).same name and same dateofBirth already exists one customer this issue coming in CBS . | we have analized the issue and replace pos fuction called in plsql procedure and fixed the issue . | No | Closed
Note on A5: • ID: A unique ID number used to identify the lesson learned in the lesson learned log.
Note on B5: • Date Identified: This column should be populated with the date that the lesson learned was identified.
Note on C5: • Entered By: This column should be populated with the name of the individual who identified the lesson learned.
Note on D5: • Subject: This column should be populated with a brief attention grabbing headline that describes the subject of the lesson learned.
Note on E5: • Situation: This column should be populated with a detailed description of the situation learned from.
Note on F5: • Lesson Learned & Recommendations: This column should be populated with a description of the lesson learned from the situation described in column E and the corrective action taken. Include recommendations regarding the outcome of the corrective action, good or bad, to help guide future project managers.
Note on G5: • Follow-Up Needed?: Indicates whether or not additional follow-up is needed.